## Cover
S-Curve & Earned Value
Plan vs actual progress with earned-value metrics — [1]
Version 0.1 · Generated 2026-09-24
Read first
This is a guided engineering calculation workbook, not a stamped design document.
Fill only yellow Input cells. Calculated and result cells are protected-by-convention (never hand-edit).
Review the Checks sheet — address any WARN or FAIL before use.
Enter governing code/table values (e.g. ampacity tables, demand factors, U-values) from your governing standard where a Source column asks for it.
Verify all results against project data and applicable standards with a qualified engineer.
Workbook structure
Inputs — every user entry (yellow).
Calculations — transparent formulas with reference IDs.
Outputs — final results (blue).
Checks — PASS/WARN/FAIL verification vs the reference limits.
Reference — sources cited by ID ([1], …).
Notes & Assumptions — declared limitations and assumptions.
Method
Plan vs actual progress with earned-value metrics
EngiMetric · https://engimetric.com

## Summary
S-Curve & Earned Value
Master verdict | WARN
Key inputs
Budget at completion (BAC) | 1000 | —
Actual completed % — now | 55 | %
Actual cost incurred (AC) | 480 | —
Planned % — period 4 | 60 | %
Key outputs
Earned value | 550 | —
SPI | 0.91667 | —
CPI | 1.1458 | —
Checks at a glance
Actual progress within range | PASS
CPI health | WARN
Version 0.1 · EngiMetric workbook library

## Inputs
Inputs — yellow cells: enter your values; source prompts governing choices
Budget at completion (BAC) | 1000 | — | estimate
Planned % — period 1 | 10 | % | baseline
Planned % — period 2 | 25 | % | baseline
Planned % — period 3 | 40 | % | baseline
Planned % — period 4 | 60 | % | baseline
Planned % — period 5 | 85 | % | baseline
Planned % — period 6 | 100 | % | baseline
Actual completed % — now | 55 | % | progress measurement
Actual cost incurred (AC) | 480 | — | cost reports

## Calculations
Calculations — transparent formulas; [n] is the reference ID (see Reference sheet)
Planned % by period 4 | 135 | % | [1]
Planned % at measurement | 60 | — | [1]
Planned value (PV) | 600 | — | [1]
Earned value (EV) | 550 | — | [1]
Actual cost (AC) | 480 | — | [1]
Schedule variance (EV − PV) | -50 | — | [1]
Cost variance (EV − AC) | 70 | — | [1]
Schedule performance index | 0.91667 | — | [1]
Cost performance index | 1.1458 | — | [1]

## Outputs
Outputs — final results (formula-driven; never hard-typed)
Earned value | 550 | — | [1]
Planned value | 600 | — | [1]
SPI | 0.91667 | — | [1]
CPI | 1.1458 | — | [1]
Schedule variance | -50 | — | [1]

## Checks
Checks — each row must land PASS (WARN acceptable when documented)
Actual progress within range | 0–100 % | PASS | [1]
CPI health | ≈ 1 | WARN | [1]
SPI health | ≈ 1 | PASS | [1]
Master verdict
Overall result | PASS when every check passes | WARN

## Reference
References
[1] | PMI PMBOK earned-value concepts (PV, EV, AC, SPI/CPI)
Equations used
Earned value | PV = BAC·planned%; EV = BAC·actual%; SPI = EV/PV; CPI = EV/AC

## Notes & Assumptions
Notes & Assumptions
1. Measurement window is period 4 of six; extend the row pattern for the full schedule.
Disclaimer
Governed by the EngiMetric Workbook Standard v1.0. Values computed depend entirely on the data entered.
Code/table-derived factors are user inputs prompted by their Source column — no copyrighted tables are embedded.
Not a substitute for qualified, licensed engineering review.